## Sheet1
ListName | TaskID | TaskSubject | TaskStartDate | TaskDueDate | TaskStatus | EstimatedTime | TaskPriority | TaskAssigneesList | TaskIsMilestone | TaskIntensity | TaskScore | TaskCreatedDate | TotalTskEstInMins | TaskExecutionDate | AssignTo | IsConflict | ConflictTimeMin | RemainingMin | AllocatedTimeMin
ClickUp | 86cw7vnxu | Mitul - Meet with AKS, Gantt Chart & its Features | 13-08-2024 | 13-08-2024 | delievered | {'hrs': 1, 'mins': 30, 'time_estimate': 5400000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 14-08-2024 11:22:17 | 90 | 13-08-2024 | Mitul Solanki | FALSE | 0 |  | 90
ClickUp | 86cw7wbej | Mitul - Prepare ERPNext HR Module Task list | 13-08-2024 | 14-08-2024 | delievered | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 14-08-2024 12:18:47 | 60 | 13-08-2024 | Mitul Solanki | FALSE | 0 |  | 60
ClickUp | 86cw7vp7r | Mitul - Prepare & Show Gantt Chart Demo | 13-08-2024 | 13-08-2024 | delievered | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | normal | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 1 | 14-08-2024 11:23:07 | 60 | 13-08-2024 | Mitul Solanki | FALSE | 0 |  | 60
|  | Mitul Solanki is available on day "13-08-2024" for 270 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 270
ERPNext | 86cw76fjj | Mitul - Compare Odoo vs Zoho vs ERPNext Solution | 14-08-2024 | 21-08-2024 | delievered | {'hrs': 0, 'mins': 30, 'time_estimate': 1800000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 12-08-2024 17:26:22 | 30 | 14-08-2024 | Mitul Solanki | FALSE | 0 |  | 30
ClickUp | 86cw7vq8k | Mitul - Prepare Doc for Standard Practices & Cons of ClickUp Gantt Chart | 14-08-2024 | 14-08-2024 | delievered | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 14-08-2024 11:25:29 | 60 | 14-08-2024 | Mitul Solanki | FALSE | 0 |  | 60
ERPNext | 86cw7wkbw | Restore V14 Data in V15 | 14-08-2024 | 16-08-2024 | delievered | {'hrs': 24, 'mins': 0, 'time_estimate': 86400000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 14-08-2024 12:34:56 | 1440 | 14-08-2024 | Mitul Solanki | FALSE | 0 |  | 390
ERPNext | 86cw7wkbw | Restore V14 Data in V15 | 14-08-2024 | 16-08-2024 | delievered | {'hrs': 24, 'mins': 0, 'time_estimate': 86400000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 14-08-2024 12:34:56 | 1050 | 15-08-2024 | Mitul Solanki | FALSE | 0 |  | 480
ERPNext | 86cw7x8v2 | Mitul - Department & Module Access | 15-08-2024 | 15-08-2024 | delievered | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 14-08-2024 13:34:34 | 60 | 15-08-2024 | Mitul Solanki | TRUE | 60 |  | 0
ERPNext | 86cw7x8vu | Mitul - Role & Permissions Setup | 15-08-2024 | 15-08-2024 | delievered | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 14-08-2024 13:34:42 | 60 | 15-08-2024 | Mitul Solanki | TRUE | 60 |  | 0
ClickUp | 86cw7vr3m | Mitul - Prepare & Show Demo for Accuvelocity Task List | 15-08-2024 | 15-08-2024 | delievered | {'hrs': 0, 'mins': 30, 'time_estimate': 1800000} | normal | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 1 | 14-08-2024 11:27:45 | 30 | 15-08-2024 | Mitul Solanki | TRUE | 30 |  | 0
ERPNext | 86cw7wkbw | Restore V14 Data in V15 | 14-08-2024 | 16-08-2024 | delievered | {'hrs': 24, 'mins': 0, 'time_estimate': 86400000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 14-08-2024 12:34:56 | 570 | 16-08-2024 | Mitul Solanki | TRUE | 90 |  | 480
ERPNext | 86cw7x7zr | Mitul - Import Customer List & Customize Form | 16-08-2024 | 16-08-2024 | delievered | {'hrs': 0, 'mins': 30, 'time_estimate': 1800000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 14-08-2024 13:31:54 | 30 | 16-08-2024 | Mitul Solanki | TRUE | 30 |  | 0
ERPNext | 86cw7xty4 | Meet with AKS | 16-08-2024 | 16-08-2024 | delievered | {'hrs': 0, 'mins': 30, 'time_estimate': 1800000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 14-08-2024 14:20:56 | 30 | 16-08-2024 | Mitul Solanki | TRUE | 30 |  | 0
ERPNext | 86cw7y1kr | Enable Streamlit Dashboard | 16-08-2024 | 16-08-2024 | delievered | {'hrs': 2, 'mins': 0, 'time_estimate': 7200000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 14-08-2024 14:43:26 | 120 | 16-08-2024 | Mitul Solanki | TRUE | 120 |  | 0
ERPNext | 86cw8arj7 | Mitul - Purchase Business Paid Plan Clickup | 16-08-2024 | 16-08-2024 | delievered | {'hrs': 0, 'mins': 15, 'time_estimate': 900000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 15-08-2024 21:29:58 | 15 | 16-08-2024 | Mitul Solanki | TRUE | 15 |  | 0
ERPNext | 86cw8atje | Stand Up Meet Task Explanation | 16-08-2024 | 16-08-2024 | delievered | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 15-08-2024 21:32:50 | 60 | 16-08-2024 | Mitul Solanki | TRUE | 60 |  | 0
ClickUp | 86cw7w79d | Mitul - Follow ClickUp Standard Practices & Show Demo AKS | 14-08-2024 | 16-08-2024 | delievered | {'hrs': 4, 'mins': 0, 'time_estimate': 14400000} | high | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 2 | 14-08-2024 12:11:00 | 240 | 16-08-2024 | Mitul Solanki | TRUE | 240 |  | 0
ClickUp | 86cw7vwm7 | AKS - Discuss Points | 14-08-2024 | 16-08-2024 | delievered | {'hrs': 0, 'mins': 15, 'time_estimate': 900000} | normal | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 1 | 14-08-2024 11:37:31 | 15 | 16-08-2024 | Mitul Solanki | TRUE | 15 |  | 0
|  | Mitul Solanki is available on day "17-08-2024" for 480 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 480
|  | Mitul Solanki is available on day "18-08-2024" for 480 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 480
ClickUp | 86cw7w8kk | Mitul - Encourage Developer Team to Follow new ClickUp Standards | 19-08-2024 | 23-08-2024 | delievered | {'hrs': 2, 'mins': 0, 'time_estimate': 7200000} | high | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 2 | 14-08-2024 12:12:37 | 120 | 19-08-2024 | Mitul Solanki | FALSE | 0 |  | 120
ClickUp | 86cw7vqyb | Mitul - Explain & Record Video for New ClickUp Standard to Developer Team | 19-08-2024 | 19-08-2024 | delievered | {'hrs': 0, 'mins': 40, 'time_estimate': 2400000} | normal | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 1 | 14-08-2024 11:27:20 | 40 | 19-08-2024 | Mitul Solanki | FALSE | 0 |  | 40
|  | Mitul Solanki is available on day "19-08-2024" for 320 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 320
|  | Mitul Solanki is available on day "20-08-2024" for 480 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 480
ERPNext | 86cw7wzx2 | Mitul - Review & Test | 21-08-2024 | 21-08-2024 | delievered | {'hrs': 0, 'mins': 30, 'time_estimate': 1800000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 14-08-2024 13:03:56 | 30 | 21-08-2024 | Mitul Solanki | FALSE | 0 |  | 30
|  | Mitul Solanki is available on day "21-08-2024" for 450 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 450
ERPNext | 86cw7wzy0 | Mitul - show demo to AKS | 22-08-2024 | 22-08-2024 | delievered | {'hrs': 0, 'mins': 30, 'time_estimate': 1800000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 14-08-2024 13:04:03 | 30 | 22-08-2024 | Mitul Solanki | FALSE | 0 |  | 30
|  | Mitul Solanki is available on day "22-08-2024" for 450 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 450
ERPNext | 86cw8atcj | Stand Up Meet Task Explanation | 23-08-2024 | 26-08-2024 | delievered | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 15-08-2024 21:32:23 | 60 | 23-08-2024 | Mitul Solanki | FALSE | 0 |  | 60
|  | Mitul Solanki is available on day "23-08-2024" for 420 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 420
|  | Mitul Solanki is available on day "24-08-2024" for 480 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 480
|  | Mitul Solanki is available on day "25-08-2024" for 480 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 480
|  | Mitul Solanki is available on day "26-08-2024" for 480 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 480
|  | Mitul Solanki is available on day "27-08-2024" for 480 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 480
|  | Mitul Solanki is available on day "28-08-2024" for 480 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 480
ERPNext | 86cw7x1eh | Mitul - Review & Test | 29-08-2024 | 30-08-2024 | delievered | {'hrs': 3, 'mins': 0, 'time_estimate': 10800000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 14-08-2024 13:09:14 | 180 | 29-08-2024 | Mitul Solanki | FALSE | 0 |  | 180
|  | Mitul Solanki is available on day "29-08-2024" for 300 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 300
ERPNext | 86cw7x1eg | Mitul - show demo to AKS | 30-08-2024 | 30-08-2024 | delievered | {'hrs': 0, 'mins': 30, 'time_estimate': 1800000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 14-08-2024 13:09:14 | 30 | 30-08-2024 | Mitul Solanki | FALSE | 0 |  | 30
AccuVelocity | 86cwbwzku | Testing | 30-08-2024 | 30-08-2024 | Open | {'hrs': 3, 'mins': 0, 'time_estimate': 10800000} | normal | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 1 | 29-08-2024 12:04:54 | 180 | 30-08-2024 | Mitul Solanki | FALSE | 0 |  | 180
|  | Mitul Solanki is available on day "30-08-2024" for 270 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 270
|  | Mitul Solanki is available on day "31-08-2024" for 480 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 480
|  | Mitul Solanki is available on day "01-09-2024" for 480 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 480
ERPNext | 86cw8atjh | Stand Up Meet Task Explanation | 02-09-2024 | 02-09-2024 | delievered | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 15-08-2024 21:32:50 | 60 | 02-09-2024 | Mitul Solanki | FALSE | 0 |  | 60
|  | Mitul Solanki is available on day "02-09-2024" for 420 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 420
ERPNext | 86cw8atvv | Mitul - Task Update Meet with AKS | 03-09-2024 | 03-09-2024 | delievered | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | normal | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 1 | 15-08-2024 21:34:24 | 60 | 03-09-2024 | Mitul Solanki | FALSE | 0 |  | 60
AccuVelocity | 86cwbx4xm | Mitul - Testing Tally API | 03-09-2024 | 03-09-2024 | in progress | {'hrs': 4, 'mins': 0, 'time_estimate': 14400000} |  | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 1 | 29-08-2024 12:17:05 | 240 | 03-09-2024 | Mitul Solanki | FALSE | 0 |  | 240
|  | Mitul Solanki is available on day "03-09-2024" for 180 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 180
ERPNext | 86cw7x1hj | Mitul - Review & Test | 04-09-2024 | 05-09-2024 | delievered | {'hrs': 3, 'mins': 0, 'time_estimate': 10800000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 14-08-2024 13:09:42 | 180 | 04-09-2024 | Mitul Solanki | FALSE | 0 |  | 180
AccuVelocity | 86cwdagvu | Mitul - Testing Implementation By Alter Different Paid Models | 04-09-2024 | 05-09-2024 | Open | {'hrs': 6, 'mins': 0, 'time_estimate': 21600000} | normal | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 1 | 03-09-2024 16:39:45 | 360 | 04-09-2024 | Mitul Solanki | FALSE | 0 |  | 300
ERPNext | 86cw7x1hg | Mitul - show demo to AKS | 05-09-2024 | 05-09-2024 | delievered | {'hrs': 0, 'mins': 30, 'time_estimate': 1800000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 14-08-2024 13:09:41 | 30 | 05-09-2024 | Mitul Solanki | FALSE | 0 |  | 30
AccuVelocity | 86cwdagvu | Mitul - Testing Implementation By Alter Different Paid Models | 04-09-2024 | 05-09-2024 | Open | {'hrs': 6, 'mins': 0, 'time_estimate': 21600000} | normal | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 1 | 03-09-2024 16:39:45 | 60 | 05-09-2024 | Mitul Solanki | FALSE | 0 |  | 60
AccuVelocity | 86cwdagxr | Mitul - Update Master API Method's | 04-09-2024 | 05-09-2024 | Open | {'hrs': 8, 'mins': 0, 'time_estimate': 28800000} | normal | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 1 | 03-09-2024 16:40:08 | 480 | 05-09-2024 | Mitul Solanki | TRUE | 90 |  | 390
AccuVelocity | 86cwdah46 | Mitul - UI Changes for Paid Model Switch in Model Page (if needed) | 06-09-2024 | 06-09-2024 | Open | {'hrs': 4, 'mins': 0, 'time_estimate': 14400000} | normal | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 1 | 03-09-2024 16:41:00 | 240 | 06-09-2024 | Mitul Solanki | FALSE | 0 |  | 240
|  | Mitul Solanki is available on day "06-09-2024" for 240 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 240
|  | Mitul Solanki is available on day "07-09-2024" for 480 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 480
|  | Mitul Solanki is available on day "08-09-2024" for 480 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 480
ERPNext | 86cwbxgru | Mitul - Stand Up Meet Task Explanation | 09-09-2024 | 09-09-2024 | delievered | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 29-08-2024 12:42:38 | 60 | 09-09-2024 | Mitul Solanki | FALSE | 0 |  | 60
AccuVelocity | 86cwetg32 | Update Set & Get Method for Template (required fields) | 09-09-2024 | 09-09-2024 | delievered | {'hrs': 1, 'mins': 30, 'time_estimate': 5400000} |  | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 1 | 09-09-2024 11:29:12 | 90 | 09-09-2024 | Mitul Solanki | FALSE | 0 |  | 90
AccuVelocity | 86cwetwwr | Get , Post, Put API - Doc Records & also store err msg column | 09-09-2024 | 09-09-2024 | delievered | {'hrs': 3, 'mins': 0, 'time_estimate': 10800000} |  | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 1 | 09-09-2024 11:43:51 | 180 | 09-09-2024 | Mitul Solanki | FALSE | 0 |  | 180
AccuVelocity | 86cweu0k4 | Discuss Mapping Process with Mitul | 09-09-2024 | 09-09-2024 | review | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} |  | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}, {'id': 67390939, 'color': '#e65100', 'email': 'dhruvin@riveredgeanalytics.com', 'initials': 'D', 'username': 'dhruvin', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390939_Fux.jpg'}] | 0 | 1 | 1 | 09-09-2024 11:51:17 | 60 | 09-09-2024 | Mitul Solanki | FALSE | 0 |  | 60
|  | Mitul Solanki is available on day "09-09-2024" for 90 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 90
ERPNext | 86cwbxgtb | Mitul - Task Update Meet with AKS | 10-09-2024 | 10-09-2024 | delievered | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | normal | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 1 | 29-08-2024 12:42:39 | 60 | 10-09-2024 | Mitul Solanki | FALSE | 0 |  | 60
|  | Mitul Solanki is available on day "10-09-2024" for 420 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 420
ERPNext | 86cwbxgtj | Mitul - Review & Test | 11-09-2024 | 12-09-2024 | delievered | {'hrs': 3, 'mins': 0, 'time_estimate': 10800000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 29-08-2024 12:42:39 | 180 | 11-09-2024 | Mitul Solanki | FALSE | 0 |  | 180
|  | Mitul Solanki is available on day "11-09-2024" for 300 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 300
ERPNext | 86cwbxgt7 | Mitul - show demo to AKS | 12-09-2024 | 12-09-2024 | delievered | {'hrs': 0, 'mins': 30, 'time_estimate': 1800000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 29-08-2024 12:42:39 | 30 | 12-09-2024 | Mitul Solanki | FALSE | 0 |  | 30
|  | Mitul Solanki is available on day "12-09-2024" for 450 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 450
|  | Mitul Solanki is available on day "13-09-2024" for 480 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 480
|  | Mitul Solanki is available on day "14-09-2024" for 480 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 480
|  | Mitul Solanki is available on day "15-09-2024" for 480 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 480
ERPNext | 86cwby8cp | Mitul - Stand Up Meet Task Explanation | 16-09-2024 | 16-09-2024 | delievered | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 29-08-2024 13:35:47 | 60 | 16-09-2024 | Mitul Solanki | FALSE | 0 |  | 60
ClickUp | 86cw8a5f9 | Mitul - Take REAL TALK on ClickUp best Practices | 16-09-2024 | 19-09-2024 | Open | {'hrs': 3, 'mins': 0, 'time_estimate': 10800000} | high | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 2 | 15-08-2024 19:54:08 | 180 | 16-09-2024 | Mitul Solanki | FALSE | 0 |  | 180
|  | Mitul Solanki is available on day "16-09-2024" for 240 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 240
ERPNext | 86cwby8ce | Mitul - Task Update Meet with AKS | 17-09-2024 | 17-09-2024 | delievered | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | normal | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 1 | 29-08-2024 13:35:47 | 60 | 17-09-2024 | Mitul Solanki | FALSE | 0 |  | 60
|  | Mitul Solanki is available on day "17-09-2024" for 420 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 420
ERPNext | 86cwby8by | Mitul - Review & Test | 18-09-2024 | 19-09-2024 | delievered | {'hrs': 3, 'mins': 0, 'time_estimate': 10800000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 29-08-2024 13:35:45 | 180 | 18-09-2024 | Mitul Solanki | FALSE | 0 |  | 180
|  | Mitul Solanki is available on day "18-09-2024" for 300 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 300
ERPNext | 86cwby8bu | Mitul - show demo to AKS | 19-09-2024 | 19-09-2024 | delievered | {'hrs': 0, 'mins': 30, 'time_estimate': 1800000} | urgent | [{'id': 67390920, 'color': '', 'email': 'mitul@riveredgeanalytics.com', 'initials': 'MS', 'username': 'Mitul Solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67390920_BGd.jpg'}] | 0 | 1 | 3 | 29-08-2024 13:35:45 | 30 | 19-09-2024 | Mitul Solanki | FALSE | 0 |  | 30
|  | Mitul Solanki is available on day "19-09-2024" for 450 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Mitul Solanki |  |  | 450