## Sheet1
ListName | TaskID | TaskSubject | TaskStartDate | TaskDueDate | TaskStatus | EstimatedTime | TaskPriority | TaskAssigneesList | TaskIsMilestone | TaskIntensity | TaskScore | TaskCreatedDate | TotalTskEstInMins | TaskExecutionDate | AssignTo | IsConflict | ConflictTimeMin | RemainingMin | AllocatedTimeMin
Drake | 86cwdjg3c | Devanshi_Prepaid Comml Insurance | 02-09-2024 | 05-09-2024 | delievered | {'hrs': 2, 'mins': 0, 'time_estimate': 7200000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:28:20 | 120 | 02-09-2024 | Devanshi | FALSE | 0 |  | 120
Drake | 86cwdjg5q | Devanshi_Goodwill Amortization | 02-09-2024 | 05-09-2024 | delievered | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:28:28 | 60 | 02-09-2024 | Devanshi | FALSE | 0 |  | 60
Drake | 86cwdjg8n | Devanshi_Depreciation (Accum Depr…...... 164700-165700) | 02-09-2024 | 05-09-2024 | delievered | {'hrs': 1, 'mins': 30, 'time_estimate': 5400000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:28:37 | 90 | 02-09-2024 | Devanshi | FALSE | 0 |  | 90
Drake | 86cwdjgaz | Devanshi_Deferred Interest-Northcoast | 02-09-2024 | 05-09-2024 | delievered | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:28:44 | 60 | 02-09-2024 | Devanshi | FALSE | 0 |  | 60
Drake | 86cwdjgeh | Devanshi_Deferred Interest-Seller\ | 02-09-2024 | 05-09-2024 | delievered | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:28:54 | 60 | 02-09-2024 | Devanshi | FALSE | 0 |  | 60
|  | Devanshi is available on day "02-09-2024" for 90 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Devanshi |  |  | 90
Drake | 86cwdjfvq | Monthly Operating Lease - Amortization | 03-09-2024 | 04-09-2024 | Open | {'hrs': 0, 'mins': 30, 'time_estimate': 1800000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:27:54 | 30 | 03-09-2024 | Devanshi | FALSE | 0 |  | 30
Drake | 86cwdjh94 | Devanshi_Accrual of Account Prism Fee in Accounting and Legal $10K - make it Reversal | 03-09-2024 | 05-09-2024 | Open | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:30:14 | 60 | 03-09-2024 | Devanshi | FALSE | 0 |  | 60
Drake | 86cwdjhft | Devanshi_Accounting and Legal (Biech Fleischman) for 2024 Audit and Tax Expense - $4K per Month. IN August Entry will be of $28K, $24K will be OOP. Refer Email : Audit & Tax Engagement Letter - 2023 | 03-09-2024 | 05-09-2024 | Open | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:30:33 | 60 | 03-09-2024 | Devanshi | FALSE | 0 |  | 60
Drake | 86cwdj761 | Devanshi_Download byline bank | 03-09-2024 | 03-09-2024 | delievered | {'hrs': 0, 'mins': 15, 'time_estimate': 900000} |  | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 1 | 04-09-2024 12:13:17 | 15 | 03-09-2024 | Devanshi | FALSE | 0 |  | 15
Drake | 86cwdj78c | Devanshi_Download Wells Frago | 03-09-2024 | 04-09-2024 | in progress | {'hrs': 0, 'mins': 15, 'time_estimate': 900000} |  | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 1 | 04-09-2024 12:13:29 | 15 | 03-09-2024 | Devanshi | FALSE | 0 |  | 15
|  | Devanshi is available on day "03-09-2024" for 300 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Devanshi |  |  | 300
Drake | 86cwbn4qx | T3 Devanshi_Liquidity report send to lenders and investors | 04-09-2024 | 04-09-2024 | Open | {'hrs': 0, 'mins': 45, 'time_estimate': 2700000} | urgent | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 3 | 3 | 28-08-2024 14:50:33 | 45 | 04-09-2024 | Devanshi | FALSE | 0 |  | 45
Drake | 86cwdj362 | T2 Devanshi_Call Users to Add there Exps | 04-09-2024 | 04-09-2024 | Open | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 2 | 2 | 04-09-2024 12:04:48 | 60 | 04-09-2024 | Devanshi | FALSE | 0 |  | 60
Drake | 86cwdj3fa | T3 Devanshi_Prepare JE for Ramp Location All Location | 04-09-2024 | 04-09-2024 | Open | {'hrs': 4, 'mins': 0, 'time_estimate': 14400000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 3 | 2 | 04-09-2024 12:05:14 | 240 | 04-09-2024 | Devanshi | FALSE | 0 |  | 240
Drake | 86cwdj5mw | Devanshi_Agency labour exps | 04-09-2024 | 04-09-2024 | Open | {'hrs': 0, 'mins': 30, 'time_estimate': 1800000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:09:14 | 30 | 04-09-2024 | Devanshi | FALSE | 0 |  | 30
Drake | 86cwdj5qu | Devanshi_Agency labour Accrual | 04-09-2024 | 04-09-2024 | Open | {'hrs': 0, 'mins': 30, 'time_estimate': 1800000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:09:31 | 30 | 04-09-2024 | Devanshi | FALSE | 0 |  | 30
Drake | 86cwdjfy0 | Accrue Monthly Real Estate Tax [DAZ-accrue/STB-Cr/Nev Ppd ] | 04-09-2024 | 04-09-2024 | Open | {'hrs': 0, 'mins': 30, 'time_estimate': 1800000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}, {'id': 73241308, 'color': '#8077f1', 'email': 'nikhil@riveredgeanalytics.com', 'initials': 'NJ', 'username': 'Nikhil Jain', 'profilePicture': None}] | 0 | 1 | 2 | 04-09-2024 12:28:03 | 30 | 04-09-2024 | Devanshi | FALSE | 0 |  | 30
Drake | 86cwdjp66 | Posting | 04-09-2024 | 04-09-2024 | Open | {'hrs': 0, 'mins': 30, 'time_estimate': 1800000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:37:16 | 30 | 04-09-2024 | Devanshi | FALSE | 0 |  | 30
Drake | 86cwawmpr | Devanshi_Ramp Detailed analysis | 04-09-2024 | 04-09-2024 | in progress | {'hrs': 4, 'mins': 0, 'time_estimate': 14400000} |  | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 1 | 26-08-2024 13:13:07 | 240 | 04-09-2024 | Devanshi | TRUE | 225 |  | 15
Drake | 86cwdj3zw | T2 Devanshi_Move Ramp Lib to DAZ | 04-09-2024 | 04-09-2024 | Open | {'hrs': 2, 'mins': 0, 'time_estimate': 7200000} | normal | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 2 | 1 | 04-09-2024 12:05:57 | 120 | 04-09-2024 | Devanshi | TRUE | 120 |  | 0
Drake | 86cwdj4h3 | Devanshi_Payroll for Each Check date | 05-09-2024 | 06-09-2024 | Open | {'hrs': 6, 'mins': 0, 'time_estimate': 21600000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:06:47 | 360 | 05-09-2024 | Devanshi | FALSE | 0 |  | 360
Drake | 86cwdj534 | T2 Devanshi_Payroll Allocation Each Location | 05-09-2024 | 06-09-2024 | Open | {'hrs': 3, 'mins': 0, 'time_estimate': 10800000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 2 | 2 | 04-09-2024 12:08:06 | 180 | 05-09-2024 | Devanshi | FALSE | 0 |  | 120
Drake | 86cwdj534 | T2 Devanshi_Payroll Allocation Each Location | 05-09-2024 | 06-09-2024 | Open | {'hrs': 3, 'mins': 0, 'time_estimate': 10800000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 2 | 2 | 04-09-2024 12:08:06 | 60 | 06-09-2024 | Devanshi | FALSE | 0 |  | 60
Drake | 86cwdj5bp | Devanshi_Payroll Accrual for leach location | 05-09-2024 | 06-09-2024 | Open | {'hrs': 2, 'mins': 30, 'time_estimate': 9000000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:08:35 | 150 | 06-09-2024 | Devanshi | FALSE | 0 |  | 150
Drake | 86cwdj5jj | Devanshi_Payroll Accrual allocation for each location | 05-09-2024 | 06-09-2024 | Open | {'hrs': 1, 'mins': 30, 'time_estimate': 5400000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:09:03 | 90 | 06-09-2024 | Devanshi | FALSE | 0 |  | 90
Drake | 86cwdjgw1 | Devanshi_Debt Issuance Costs Amortization [UPDATE for LGC invoice pmt in Dec ] | 06-09-2024 | 06-09-2024 | Open | {'hrs': 2, 'mins': 30, 'time_estimate': 9000000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:29:28 | 150 | 06-09-2024 | Devanshi | FALSE | 0 |  | 150
|  | Devanshi is available on day "06-09-2024" for 30 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Devanshi |  |  | 30
|  | Devanshi is available on day "07-09-2024" for 480 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Devanshi |  |  | 480
|  | Devanshi is available on day "08-09-2024" for 480 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Devanshi |  |  | 480
Drake | 86cwdj7kx | T3 Devanshi_Bal Trans to Multiple location | 09-09-2024 | 09-09-2024 | Open | {'hrs': 2, 'mins': 0, 'time_estimate': 7200000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 3 | 2 | 04-09-2024 12:14:14 | 120 | 09-09-2024 | Devanshi | FALSE | 0 |  | 120
Drake | 86cwdjfr8 | Xfr Sales Tax to DAZ where paid | 09-09-2024 | 09-09-2024 | Open | {'hrs': 2, 'mins': 0, 'time_estimate': 7200000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:27:45 | 120 | 09-09-2024 | Devanshi | FALSE | 0 |  | 120
Drake | 86cwdjgpr | Devanshi_Inventory adjustments to SAGE module and YE counts | 09-09-2024 | 11-09-2024 | Open | {'hrs': 5, 'mins': 0, 'time_estimate': 18000000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:29:13 | 300 | 09-09-2024 | Devanshi | FALSE | 0 |  | 240
Drake | 86cwdjgpr | Devanshi_Inventory adjustments to SAGE module and YE counts | 09-09-2024 | 11-09-2024 | Open | {'hrs': 5, 'mins': 0, 'time_estimate': 18000000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:29:13 | 60 | 10-09-2024 | Devanshi | FALSE | 0 |  | 60
Drake | 86cwdjgt5 | Devanshi_Intercompany Sales-COGS Adj per schedule | 09-09-2024 | 11-09-2024 | Open | {'hrs': 3, 'mins': 0, 'time_estimate': 10800000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:29:20 | 180 | 10-09-2024 | Devanshi | FALSE | 0 |  | 180
Drake | 86cwdjh3h | Devanshi_Interco Sales | 10-09-2024 | 12-09-2024 | Open | {'hrs': 4, 'mins': 0, 'time_estimate': 14400000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:29:56 | 240 | 10-09-2024 | Devanshi | FALSE | 0 |  | 240
Drake | 86cwdjhuh | Devanshi_Recording of July Missed Payroll of Direct Labor - We will show it as Out of Period Expense | 10-09-2024 | 10-09-2024 | Open | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:31:06 | 60 | 10-09-2024 | Devanshi | TRUE | 60 |  | 0
Drake | 86cwdjhxg | Devanshi_Reverse Sage Annual Expense Entry, move it to prepaid and then amortize over 12 months | 10-09-2024 | 10-09-2024 | Open | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:31:15 | 60 | 10-09-2024 | Devanshi | TRUE | 60 |  | 0
Drake | 86cwdjj1e | Devanshi_Salt Creek Management Fee Calculations based on July Financials and Accrue based on Last 12 months EBITDA Calculations | 10-09-2024 | 10-09-2024 | Open | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:31:23 | 60 | 10-09-2024 | Devanshi | TRUE | 60 |  | 0
Drake | 86cwdjy04 | Devanshi_Financial Pckg | 11-09-2024 | 13-09-2024 | Open | {'hrs': 10, 'mins': 0, 'time_estimate': 36000000} | urgent | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 3 | 04-09-2024 12:51:24 | 600 | 11-09-2024 | Devanshi | FALSE | 0 |  | 480
Drake | 86cwdr0u7 | Devanshi_Liquidity report send to lenders and investors | 11-09-2024 | 11-09-2024 | Open | {'hrs': 0, 'mins': 45, 'time_estimate': 2700000} | urgent | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 3 | 04-09-2024 23:02:38 | 45 | 11-09-2024 | Devanshi | TRUE | 45 |  | 0
Drake | 86cwdjy04 | Devanshi_Financial Pckg | 11-09-2024 | 13-09-2024 | Open | {'hrs': 10, 'mins': 0, 'time_estimate': 36000000} | urgent | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 3 | 04-09-2024 12:51:24 | 120 | 12-09-2024 | Devanshi | FALSE | 0 |  | 120
Drake | 86cwdjy6q | Devanshi_Financial Workbook | 11-09-2024 | 13-09-2024 | Open | {'hrs': 10, 'mins': 0, 'time_estimate': 36000000} | urgent | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 3 | 04-09-2024 12:51:42 | 600 | 12-09-2024 | Devanshi | FALSE | 0 |  | 360
Drake | 86cwdjgk8 | Devanshi_SCC Fees Accrual calc cautght up as of yearend | 11-09-2024 | 12-09-2024 | Open | {'hrs': 3, 'mins': 0, 'time_estimate': 10800000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 12:29:03 | 180 | 12-09-2024 | Devanshi | TRUE | 180 |  | 0
Drake | 86cwdjy6q | Devanshi_Financial Workbook | 11-09-2024 | 13-09-2024 | Open | {'hrs': 10, 'mins': 0, 'time_estimate': 36000000} | urgent | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 3 | 04-09-2024 12:51:42 | 240 | 13-09-2024 | Devanshi | FALSE | 0 |  | 240
Drake | 86cwdjybe | Devanshi_SG&A | 11-09-2024 | 13-09-2024 | Open | {'hrs': 8, 'mins': 0, 'time_estimate': 28800000} | urgent | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 3 | 04-09-2024 12:51:54 | 480 | 13-09-2024 | Devanshi | TRUE | 240 |  | 240
Drake | 86cwdjyjj | Devanshi_other reports | 13-09-2024 | 13-09-2024 | Open | {'hrs': 3, 'mins': 0, 'time_estimate': 10800000} | urgent | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 3 | 04-09-2024 12:52:18 | 180 | 13-09-2024 | Devanshi | TRUE | 180 |  | 0
Drake | 86cw9fuyy | Devanshi_BBCReport Prepartion | 13-09-2024 | 13-09-2024 | Open | {'hrs': 3, 'mins': 0, 'time_estimate': 10800000} |  | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 1 | 20-08-2024 13:24:11 | 180 | 13-09-2024 | Devanshi | TRUE | 180 |  | 0
Drake | 86cw9fv4g | Devanshi_BBC Report Review and Submittion | 13-09-2024 | 13-09-2024 | Open | {'hrs': 1, 'mins': 0, 'time_estimate': 3600000} |  | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 1 | 20-08-2024 13:24:41 | 60 | 13-09-2024 | Devanshi | TRUE | 60 |  | 0
Drake | 86cwdjydv | Devanshi_JE review | 12-09-2024 | 16-09-2024 | Open | {'hrs': 16, 'mins': 0, 'time_estimate': 57600000} | urgent | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 3 | 04-09-2024 12:52:02 | 960 | 14-09-2024 | Devanshi | FALSE | 0 |  | 480
Drake | 86cwdjydv | Devanshi_JE review | 12-09-2024 | 16-09-2024 | Open | {'hrs': 16, 'mins': 0, 'time_estimate': 57600000} | urgent | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 3 | 04-09-2024 12:52:02 | 480 | 15-09-2024 | Devanshi | FALSE | 0 |  | 480
IKIO - COGSAnalyzer | 86cwdmtku | Devanshi_Ask Damini for Data | 16-09-2024 | 20-09-2024 | Open | {'hrs': 1, 'mins': 30, 'time_estimate': 5400000} | urgent | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 3 | 04-09-2024 14:08:41 | 90 | 16-09-2024 | Devanshi | FALSE | 0 |  | 90
Airen group - Customer List | 86cwdm12v | Devanshi_Testing and Submittion | 09-09-2024 | 18-09-2024 | Open | {'hrs': 6, 'mins': 0, 'time_estimate': 21600000} | high | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 2 | 04-09-2024 13:32:30 | 360 | 16-09-2024 | Devanshi | FALSE | 0 |  | 360
|  | Devanshi is available on day "16-09-2024" for 30 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Devanshi |  |  | 30
|  | Devanshi is available on day "17-09-2024" for 480 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Devanshi |  |  | 480
Drake | 86cwfnkup | Devanshi_Liquidity report send to lenders and investors | 18-09-2024 | 18-09-2024 | Open | {'hrs': 0, 'mins': 45, 'time_estimate': 2700000} | urgent | [{'id': 67391042, 'color': '#cddc39', 'email': 'devanshi@riveredgeanalytics.com', 'initials': 'D', 'username': 'Devanshi', 'profilePicture': 'https://attachments.clickup.com/profilePictures/67391042_5Q4.jpg'}] | 0 | 1 | 3 | 11-09-2024 23:04:57 | 45 | 18-09-2024 | Devanshi | FALSE | 0 |  | 45
|  | Devanshi is available on day "18-09-2024" for 435 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Devanshi |  |  | 435
|  | Devanshi is available on day "19-09-2024" for 480 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Devanshi |  |  | 480
|  | Devanshi is available on day "20-09-2024" for 480 minutes. |  |  |  | {} |  | [] | 0 | 0 | 0 |  | 0 |  | Devanshi |  |  | 480