## Sheet1
ListName | ListID | FolderName | SpaceID | TaskID | TaskSubject | TaskStartDate | TaskDueDate | ParentTaskID | EstimatedTime | TaskPriority | TaskStatus | AssignByPersonDetails | TaskAssigneesList | WatchersList | TaskCreatedDate | TaskUpdateDate | TaskDateClosed | TaskDateDone | TaskTags | TaskDependencies | TaskIsMilestone | TaskIntensity | TaskCheckLists | TaskScore
ERPNext | 901600183071 | REAL Office | 90020386592 | 86cw7x8f4 | Customize Inbuilt Form | 2024-08-15 | 15-08-2024 | 86cw7wkbw | {"hrs": 8, "mins": 0, "time_estimate": 28800000} | {'id': '1', 'color': '#f50000', 'priority': 'urgent', 'orderindex': '1'} | {"id": "subcat901600183071_subcat901600182452_subcat900202016677_subcat900202016557_subcat900202016465_subcat900201647299_subcat900201617233_subcat900201614169_subcat900201614016_subcat900201613908_subcat900201524923_subcat900900756278_subcat900900756275_subcat900900756272_subcat900600588774_sc900600504232_NTf0x6rB", "type": "closed", "color": "#008844", "status": "delievered", "orderindex": 4} | {"id": 67390920, "color": "", "email": "mitul@riveredgeanalytics.com", "username": "Mitul Solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/67390920_BGd.jpg"} | [{'id': 88895068, 'color': '#622aea', 'email': 'mansi@riveredgeanalytics.com', 'initials': 'MS', 'username': 'mansi solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/88895068_IUP.jpg'}] | [{"id": 67390920, "color": "", "email": "mitul@riveredgeanalytics.com", "initials": "MS", "username": "Mitul Solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/67390920_BGd.jpg"}, {"id": 67391743, "color": "#81b1ff", "email": "harshil@riveredgeanalytics.com", "initials": "H", "username": "Harshil", "profilePicture": "https://attachments.clickup.com/profilePictures/67391743_8EA.jpg"}, {"id": 88895068, "color": "#622aea", "email": "mansi@riveredgeanalytics.com", "initials": "MS", "username": "mansi solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/88895068_IUP.jpg"}] | 14-08-2024 | 02-09-2024 | 23-08-2024 | 23-08-2024 | [] | [] | 0 | 1 | [] | 3
ERPNext | 901600183071 | REAL Office | 90020386592 | 86cw7x7xw | Mansi - Import Projects List | 2024-08-16 | 16-08-2024 | 86cw7x99c | {"hrs": 1, "mins": 0, "time_estimate": 3600000} | {'id': '1', 'color': '#f50000', 'priority': 'urgent', 'orderindex': '1'} | {"id": "subcat901600183071_subcat901600182452_subcat900202016677_subcat900202016557_subcat900202016465_subcat900201647299_subcat900201617233_subcat900201614169_subcat900201614016_subcat900201613908_subcat900201524923_subcat900900756278_subcat900900756275_subcat900900756272_subcat900600588774_sc900600504232_NTf0x6rB", "type": "closed", "color": "#008844", "status": "delievered", "orderindex": 4} | {"id": 67390920, "color": "", "email": "mitul@riveredgeanalytics.com", "username": "Mitul Solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/67390920_BGd.jpg"} | [{'id': 88895068, 'color': '#622aea', 'email': 'mansi@riveredgeanalytics.com', 'initials': 'MS', 'username': 'mansi solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/88895068_IUP.jpg'}] | [{"id": 67390920, "color": "", "email": "mitul@riveredgeanalytics.com", "initials": "MS", "username": "Mitul Solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/67390920_BGd.jpg"}, {"id": 67391743, "color": "#81b1ff", "email": "harshil@riveredgeanalytics.com", "initials": "H", "username": "Harshil", "profilePicture": "https://attachments.clickup.com/profilePictures/67391743_8EA.jpg"}, {"id": 88895068, "color": "#622aea", "email": "mansi@riveredgeanalytics.com", "initials": "MS", "username": "mansi solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/88895068_IUP.jpg"}] | 14-08-2024 | 02-09-2024 | 23-08-2024 | 23-08-2024 | [] | [] | 0 | 1 | [] | 3
ERPNext | 901600183071 | REAL Office | 90020386592 | 86cw7x84y | Vishal - Import Timesheets | 2024-08-16 | 16-08-2024 | 86cw7x99c | {"hrs": 3, "mins": 0, "time_estimate": 10800000} | {'id': '1', 'color': '#f50000', 'priority': 'urgent', 'orderindex': '1'} | {"id": "subcat901600183071_subcat901600182452_subcat900202016677_subcat900202016557_subcat900202016465_subcat900201647299_subcat900201617233_subcat900201614169_subcat900201614016_subcat900201613908_subcat900201524923_subcat900900756278_subcat900900756275_subcat900900756272_subcat900600588774_sc900600504232_NTf0x6rB", "type": "closed", "color": "#008844", "status": "delievered", "orderindex": 4} | {"id": 67390920, "color": "", "email": "mitul@riveredgeanalytics.com", "username": "Mitul Solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/67390920_BGd.jpg"} | [{'id': 88895068, 'color': '#622aea', 'email': 'mansi@riveredgeanalytics.com', 'initials': 'MS', 'username': 'mansi solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/88895068_IUP.jpg'}] | [{"id": 67391743, "color": "#81b1ff", "email": "harshil@riveredgeanalytics.com", "initials": "H", "username": "Harshil", "profilePicture": "https://attachments.clickup.com/profilePictures/67391743_8EA.jpg"}, {"id": 67390920, "color": "", "email": "mitul@riveredgeanalytics.com", "initials": "MS", "username": "Mitul Solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/67390920_BGd.jpg"}, {"id": 88895068, "color": "#622aea", "email": "mansi@riveredgeanalytics.com", "initials": "MS", "username": "mansi solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/88895068_IUP.jpg"}] | 14-08-2024 | 02-09-2024 | 23-08-2024 | 23-08-2024 | [] | [] | 0 | 1 | [] | 3
ERPNext | 901600183071 | REAL Office | 90020386592 | 86cw7x9jk | Test V15 Implementation | 2024-08-16 | 16-08-2024 | 86cw7wkbw | {"hrs": 4, "mins": 0, "time_estimate": 14400000} | {'id': '1', 'color': '#f50000', 'priority': 'urgent', 'orderindex': '1'} | {"id": "subcat901600183071_subcat901600182452_subcat900202016677_subcat900202016557_subcat900202016465_subcat900201647299_subcat900201617233_subcat900201614169_subcat900201614016_subcat900201613908_subcat900201524923_subcat900900756278_subcat900900756275_subcat900900756272_subcat900600588774_sc900600504232_NTf0x6rB", "type": "closed", "color": "#008844", "status": "delievered", "orderindex": 4} | {"id": 67390920, "color": "", "email": "mitul@riveredgeanalytics.com", "username": "Mitul Solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/67390920_BGd.jpg"} | [{'id': 96776599, 'color': '', 'email': 'mohit.intern@riveredgeanalytics.com', 'initials': 'MP', 'username': 'Mohit parmar', 'profilePicture': None}, {'id': 88895068, 'color': '#622aea', 'email': 'mansi@riveredgeanalytics.com', 'initials': 'MS', 'username': 'mansi solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/88895068_IUP.jpg'}] | [{"id": 67391743, "color": "#81b1ff", "email": "harshil@riveredgeanalytics.com", "initials": "H", "username": "Harshil", "profilePicture": "https://attachments.clickup.com/profilePictures/67391743_8EA.jpg"}, {"id": 67390920, "color": "", "email": "mitul@riveredgeanalytics.com", "initials": "MS", "username": "Mitul Solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/67390920_BGd.jpg"}, {"id": 88895068, "color": "#622aea", "email": "mansi@riveredgeanalytics.com", "initials": "MS", "username": "mansi solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/88895068_IUP.jpg"}] | 14-08-2024 | 02-09-2024 | 23-08-2024 | 23-08-2024 | [] | [] | 0 | 1 | [] | 3
ERPNext | 901600183071 | REAL Office | 90020386592 | 86cw7xy24 | Mansi - Enable Client & Pyhton Scripts | 2024-08-16 | 16-08-2024 | 86cw7wkbw | {"hrs": 3, "mins": 0, "time_estimate": 10800000} | {'id': '1', 'color': '#f50000', 'priority': 'urgent', 'orderindex': '1'} | {"id": "subcat901600183071_subcat901600182452_subcat900202016677_subcat900202016557_subcat900202016465_subcat900201647299_subcat900201617233_subcat900201614169_subcat900201614016_subcat900201613908_subcat900201524923_subcat900900756278_subcat900900756275_subcat900900756272_subcat900600588774_sc900600504232_NTf0x6rB", "type": "closed", "color": "#008844", "status": "delievered", "orderindex": 4} | {"id": 67390920, "color": "", "email": "mitul@riveredgeanalytics.com", "username": "Mitul Solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/67390920_BGd.jpg"} | [{'id': 88895068, 'color': '#622aea', 'email': 'mansi@riveredgeanalytics.com', 'initials': 'MS', 'username': 'mansi solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/88895068_IUP.jpg'}] | [{"id": 88895068, "color": "#622aea", "email": "mansi@riveredgeanalytics.com", "initials": "MS", "username": "mansi solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/88895068_IUP.jpg"}, {"id": 67390920, "color": "", "email": "mitul@riveredgeanalytics.com", "initials": "MS", "username": "Mitul Solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/67390920_BGd.jpg"}, {"id": 67391743, "color": "#81b1ff", "email": "harshil@riveredgeanalytics.com", "initials": "H", "username": "Harshil", "profilePicture": "https://attachments.clickup.com/profilePictures/67391743_8EA.jpg"}] | 14-08-2024 | 02-09-2024 | 23-08-2024 | 23-08-2024 | [] | [] | 0 | 1 | [] | 3
ERPNext | 901600183071 | REAL Office | 90020386592 | 86cw7y1dr | Test Individual Any 3-4 User Accounts | 2024-08-16 | 16-08-2024 | 86cw7x9jk | {"hrs": 3, "mins": 0, "time_estimate": 10800000} | {'id': '1', 'color': '#f50000', 'priority': 'urgent', 'orderindex': '1'} | {"id": "subcat901600183071_subcat901600182452_subcat900202016677_subcat900202016557_subcat900202016465_subcat900201647299_subcat900201617233_subcat900201614169_subcat900201614016_subcat900201613908_subcat900201524923_subcat900900756278_subcat900900756275_subcat900900756272_subcat900600588774_sc900600504232_NTf0x6rB", "type": "closed", "color": "#008844", "status": "delievered", "orderindex": 4} | {"id": 67390920, "color": "", "email": "mitul@riveredgeanalytics.com", "username": "Mitul Solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/67390920_BGd.jpg"} | [{'id': 88895068, 'color': '#622aea', 'email': 'mansi@riveredgeanalytics.com', 'initials': 'MS', 'username': 'mansi solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/88895068_IUP.jpg'}] | [{"id": 88895068, "color": "#622aea", "email": "mansi@riveredgeanalytics.com", "initials": "MS", "username": "mansi solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/88895068_IUP.jpg"}, {"id": 67390920, "color": "", "email": "mitul@riveredgeanalytics.com", "initials": "MS", "username": "Mitul Solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/67390920_BGd.jpg"}, {"id": 67391743, "color": "#81b1ff", "email": "harshil@riveredgeanalytics.com", "initials": "H", "username": "Harshil", "profilePicture": "https://attachments.clickup.com/profilePictures/67391743_8EA.jpg"}] | 14-08-2024 | 02-09-2024 | 23-08-2024 | 23-08-2024 | [] | [] | 0 | 1 | [] | 3
ERPNext | 901600183071 | REAL Office | 90020386592 | 86cw75tb6 | Mohit - Job Openings Form | 2024-08-20 | 22-08-2024 | 86cw76fxd | {"hrs": 5, "mins": 0, "time_estimate": 18000000} | {'id': '1', 'color': '#f50000', 'priority': 'urgent', 'orderindex': '1'} | {"id": "subcat901600183071_subcat901600182452_subcat900202016677_subcat900202016557_subcat900202016465_subcat900201647299_subcat900201617233_subcat900201614169_subcat900201614016_subcat900201613908_subcat900201524923_subcat900900756278_subcat900900756275_subcat900900756272_subcat900600588774_sc900600504232_NTf0x6rB", "type": "closed", "color": "#008844", "status": "delievered", "orderindex": 4} | {"id": 67390920, "color": "", "email": "mitul@riveredgeanalytics.com", "username": "Mitul Solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/67390920_BGd.jpg"} | [{'id': 88895068, 'color': '#622aea', 'email': 'mansi@riveredgeanalytics.com', 'initials': 'MS', 'username': 'mansi solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/88895068_IUP.jpg'}] | [{"id": 67390920, "color": "", "email": "mitul@riveredgeanalytics.com", "initials": "MS", "username": "Mitul Solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/67390920_BGd.jpg"}, {"id": 88895068, "color": "#622aea", "email": "mansi@riveredgeanalytics.com", "initials": "MS", "username": "mansi solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/88895068_IUP.jpg"}] | 12-08-2024 | 02-09-2024 | 29-08-2024 | 29-08-2024 | [] | [{"type": 1, "userid": "67390920", "task_id": "86cw75tb6", "chain_id": null, "depends_on": "86cw73j5j", "date_created": "1723621006884", "workspace_id": "9002161791"}, {"type": 1, "userid": "67390920", "task_id": "86cw75tb6", "chain_id": null, "depends_on": "86cw7wu4q", "date_created": "1723619983818", "workspace_id": "9002161791"}, {"type": 1, "userid": "67390920", "task_id": "86cw7wzx2", "chain_id": null, "depends_on": "86cw75tb6", "date_created": "1723621933695", "workspace_id": "9002161791"}] | 0 | 1 | [] | 3
ERPNext | 901600183071 | REAL Office | 90020386592 | 86cw75tdf | Mansi - Leave Request Form | 2024-08-21 | 30-08-2024 | 86cw7ngwc | {"hrs": 16, "mins": 0, "time_estimate": 57600000} | {'id': '1', 'color': '#f50000', 'priority': 'urgent', 'orderindex': '1'} | {"id": "subcat901600183071_subcat901600182452_subcat900202016677_subcat900202016557_subcat900202016465_subcat900201647299_subcat900201617233_subcat900201614169_subcat900201614016_subcat900201613908_subcat900201524923_subcat900900756278_subcat900900756275_subcat900900756272_subcat900600588774_sc900600504232_NTf0x6rB", "type": "closed", "color": "#008844", "status": "delievered", "orderindex": 4} | {"id": 67390920, "color": "", "email": "mitul@riveredgeanalytics.com", "username": "Mitul Solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/67390920_BGd.jpg"} | [{'id': 88895068, 'color': '#622aea', 'email': 'mansi@riveredgeanalytics.com', 'initials': 'MS', 'username': 'mansi solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/88895068_IUP.jpg'}] | [{"id": 67390920, "color": "", "email": "mitul@riveredgeanalytics.com", "initials": "MS", "username": "Mitul Solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/67390920_BGd.jpg"}, {"id": 88895068, "color": "#622aea", "email": "mansi@riveredgeanalytics.com", "initials": "MS", "username": "mansi solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/88895068_IUP.jpg"}] | 12-08-2024 | 06-09-2024 | 06-09-2024 | 06-09-2024 | [] | [{"type": 1, "userid": "67390920", "task_id": "86cw75tdf", "chain_id": null, "depends_on": "86cw7wt1j", "date_created": "1723619922569", "workspace_id": "9002161791"}, {"type": 1, "userid": "67390920", "task_id": "86cw75tdf", "chain_id": null, "depends_on": "86cw7wxq8", "date_created": "1724921601295", "workspace_id": "9002161791"}] | 0 | 1 | [] | 3
ERPNext | 901600183071 | REAL Office | 90020386592 | 86cwa53ct | Mansi - Job Opening Form Suggestions | 2024-08-29 | 29-08-2024 | 86cw7ngbk | {"hrs": 4, "mins": 0, "time_estimate": 14400000} | {'id': '3', 'color': '#6fddff', 'priority': 'normal', 'orderindex': '3'} | {"id": "subcat901600183071_subcat901600182452_subcat900202016677_subcat900202016557_subcat900202016465_subcat900201647299_subcat900201617233_subcat900201614169_subcat900201614016_subcat900201613908_subcat900201524923_subcat900900756278_subcat900900756275_subcat900900756272_subcat900600588774_sc900600504232_NTf0x6rB", "type": "closed", "color": "#008844", "status": "delievered", "orderindex": 4} | {"id": 67390920, "color": "", "email": "mitul@riveredgeanalytics.com", "username": "Mitul Solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/67390920_BGd.jpg"} | [{'id': 88895068, 'color': '#622aea', 'email': 'mansi@riveredgeanalytics.com', 'initials': 'MS', 'username': 'mansi solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/88895068_IUP.jpg'}] | [{"id": 88895068, "color": "#622aea", "email": "mansi@riveredgeanalytics.com", "initials": "MS", "username": "mansi solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/88895068_IUP.jpg"}, {"id": 67390920, "color": "", "email": "mitul@riveredgeanalytics.com", "initials": "MS", "username": "Mitul Solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/67390920_BGd.jpg"}, {"id": 67391743, "color": "#81b1ff", "email": "harshil@riveredgeanalytics.com", "initials": "H", "username": "Harshil", "profilePicture": "https://attachments.clickup.com/profilePictures/67391743_8EA.jpg"}] | 22-08-2024 | 03-09-2024 | 03-09-2024 | 03-09-2024 | [] | [] | 0 | 1 | [] | 1
ERPNext | 901600183071 | REAL Office | 90020386592 | 86cwbxkvd | Mansi - Create New Member Accounts | 2024-08-29 | 30-08-2024 | 86cw7ngbk | {"hrs": 0, "mins": 20, "time_estimate": 1200000} | {'id': '3', 'color': '#6fddff', 'priority': 'normal', 'orderindex': '3'} | {"id": "subcat901600183071_subcat901600182452_subcat900202016677_subcat900202016557_subcat900202016465_subcat900201647299_subcat900201617233_subcat900201614169_subcat900201614016_subcat900201613908_subcat900201524923_subcat900900756278_subcat900900756275_subcat900900756272_subcat900600588774_sc900600504232_NTf0x6rB", "type": "closed", "color": "#008844", "status": "delievered", "orderindex": 4} | {"id": 67390920, "color": "", "email": "mitul@riveredgeanalytics.com", "username": "Mitul Solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/67390920_BGd.jpg"} | [{'id': 88895068, 'color': '#622aea', 'email': 'mansi@riveredgeanalytics.com', 'initials': 'MS', 'username': 'mansi solanki', 'profilePicture': 'https://attachments.clickup.com/profilePictures/88895068_IUP.jpg'}] | [{"id": 88895068, "color": "#622aea", "email": "mansi@riveredgeanalytics.com", "initials": "MS", "username": "mansi solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/88895068_IUP.jpg"}, {"id": 67390920, "color": "", "email": "mitul@riveredgeanalytics.com", "initials": "MS", "username": "Mitul Solanki", "profilePicture": "https://attachments.clickup.com/profilePictures/67390920_BGd.jpg"}, {"id": 67391743, "color": "#81b1ff", "email": "harshil@riveredgeanalytics.com", "initials": "H", "username": "Harshil", "profilePicture": "https://attachments.clickup.com/profilePictures/67391743_8EA.jpg"}] | 29-08-2024 | 03-09-2024 | 03-09-2024 | 03-09-2024 | [] | [] | 0 | 1 | [] | 1